## Sprint Backlog Extract
Sprint ID | Task ID | Task Description | Estimated Effort (Hours) | Status
SP-01 | T-101 | Design DDL for users, patients, doctors, departments, rooms, appointments, payments | 10 | Done
SP-01 | T-102 | Add Postgres EXCLUDE constraints for doctor and room overlap | 6 | Done
SP-01 | T-103 | Create JPA entities with Hibernate Validator annotations | 12 | Done
SP-01 | T-104 | Registration API with unique email check | 8 | Done
SP-01 | T-105 | Registration form with confirm password and strong password rules | 10 | Done
SP-01 | T-106 | JWT issue and validation filter | 10 | Done
SP-01 | T-107 | Spring Security config with role based URL rules | 8 | Done
SP-01 | T-108 | Angular auth service, token interceptor and route guards | 10 | Done
SP-01 | T-109 | Public doctor and department endpoints with search | 6 | Done
SP-01 | T-110 | Landing page with specialists and departments tables | 10 | Done
SP-01 | T-111 | DataSeeder with admin, 3 departments, 4 doctors, 4 rooms | 4 | Done
SP-01 | T-112 | Smoke test pack for auth and public endpoints | 6 | Done
SP-02 | T-201 | Slot generation from doctor availability and slot length | 10 | Done
SP-02 | T-202 | Slot picker UI with availability markers | 8 | Done
SP-02 | T-203 | Collision validation service for doctor overlap | 10 | Done
SP-02 | T-204 | Room occupancy validation and free-room endpoint | 8 | Done
SP-02 | T-205 | Concurrency test - two bookings for the same slot | 8 | Done
SP-02 | T-206 | Booking API returning PENDING appointment | 8 | Done
SP-02 | T-207 | Booking page with room preference and reason | 10 | Done
SP-02 | T-208 | Patient dashboard with appointment table and live status | 10 | Done
SP-02 | T-209 | PaymentService abstraction and pending payment on booking | 6 | Done
SP-02 | T-210 | Card payment endpoint - Luhn check, store last 4 digits only | 10 | Done
SP-02 | T-211 | Payment page with masked card input and terms checkbox | 10 | Done
SP-02 | T-212 | Printable receipt view with print stylesheet | 8 | Done
SP-02 | T-213 | Cancel flow with automatic refund and admin remark | 8 | Done
SP-03 | T-301 | Approve and reject endpoints with mandatory remarks | 8 | Done
SP-03 | T-302 | Request queue table with inline actions and room assignment | 10 | Done
SP-03 | T-303 | Admin CRUD endpoints and validation rules | 12 | Done
SP-03 | T-304 | Six-tab admin dashboard with forms and tables | 14 | Done
SP-03 | T-305 | Doctor years of experience field end to end | 4 | Done
SP-03 | T-306 | Search bars - appointment ID/date, doctor ID/specialty, patient ID/date | 10 | Done
SP-03 | T-307 | Bulk delete endpoints and multi-select tables | 8 | Done
SP-03 | T-308 | Patient status field with auto-discharge rule | 8 | Done
SP-03 | T-309 | Status column with admit and discharge actions | 6 | Done
SP-03 | T-310 | Global exception handler and error flattening | 6 | Done
SP-03 | T-311 | Popup service for success and error dialogs | 6 | Done
SP-03 | T-312 | Native CSS theme, logo and navbar with home button | 10 | Done
SP-03 | T-313 | Responsive checks and print stylesheet QA | 6 | Done
SP-03 | T-314 | Regression pass across all roles | 8 | Done
SP-03 | T-315 | README, user manual and flowchart pack | 8 | Done
Source: SprintBacklog.xlsx > 'Sprint Backlog' sheet (columns Sprint ID, Task ID, Task Description, Estimated Effort, Status), copied here so this workbook has no external links. Re-copy after changing the backlog.

## SP-01 Burndown
Sprint 1 - Foundation & Authentication - Burndown Chart
Sprint window: 2026-06-01 to 2026-06-12
Total committed effort (h) | 100
Sprint length (working days) | 10
Ideal burn rate (h/day) | 10
Sprint Day | Ideal Remaining (h) | Effort Completed (h) | Actual Remaining (h)
0 | 100 | 0 | 100
1 | 90 | 0 | 100
2 | 80 | 6 | 94
3 | 70 | 10 | 84
4 | 60 | 12 | 72
5 | 50 | 8 | 64
6 | 40 | 4 | 60
7 | 30 | 12 | 48
8 | 20 | 14 | 34
9 | 10 | 16 | 18
10 | 0 | 18 | 0
Total |  | 100
Blue figures in 'Effort Completed' are the only inputs - they come from the daily stand-up. Ideal and Actual Remaining are formulas; the ideal line drops by the burn rate in B6 each day, the actual line subtracts the effort actually closed.

## SP-02 Burndown
Sprint 2 - Booking, Collision & Payment - Burndown Chart
Sprint window: 2026-06-15 to 2026-06-26
Total committed effort (h) | 114
Sprint length (working days) | 10
Ideal burn rate (h/day) | 11.4
Sprint Day | Ideal Remaining (h) | Effort Completed (h) | Actual Remaining (h)
0 | 114 | 0 | 114
1 | 102.6 | 4 | 110
2 | 91.2 | 8 | 102
3 | 79.8 | 12 | 90
4 | 68.4 | 14 | 76
5 | 57 | 10 | 66
6 | 45.6 | 6 | 60
7 | 34.2 | 14 | 46
8 | 22.8 | 16 | 30
9 | 11.4 | 14 | 16
10 | 0 | 16 | 0
Total |  | 114
Blue figures in 'Effort Completed' are the only inputs - they come from the daily stand-up. Ideal and Actual Remaining are formulas; the ideal line drops by the burn rate in B6 each day, the actual line subtracts the effort actually closed.

## SP-03 Burndown
Sprint 3 - Admin Console, Search & UI - Burndown Chart
Sprint window: 2026-06-29 to 2026-07-10
Total committed effort (h) | 124
Sprint length (working days) | 10
Ideal burn rate (h/day) | 12.4
Sprint Day | Ideal Remaining (h) | Effort Completed (h) | Actual Remaining (h)
0 | 124 | 0 | 124
1 | 111.6 | 6 | 118
2 | 99.2 | 10 | 108
3 | 86.8 | 14 | 94
4 | 74.4 | 16 | 78
5 | 62 | 12 | 66
6 | 49.6 | 8 | 58
7 | 37.2 | 14 | 44
8 | 24.8 | 16 | 28
9 | 12.4 | 14 | 14
10 | 0 | 14 | 0
Total |  | 124
Blue figures in 'Effort Completed' are the only inputs - they come from the daily stand-up. Ideal and Actual Remaining are formulas; the ideal line drops by the burn rate in B6 each day, the actual line subtracts the effort actually closed.

## Notes
Burndown Chart - how to read it
Axes | X-axis = sprint day (0 to 10 working days). Y-axis = remaining effort in hours.
Ideal Burn Line | Grey dashed line. Straight drop from the committed total to zero at an even burn rate (total effort / sprint length).
Actual Burn Line | Solid blue line. Committed total minus the effort actually closed each day, taken from the daily stand-up.
Data source | 'Sprint Backlog Extract' sheet, copied from SprintBacklog.xlsx. Sprint totals are SUMIFS over that extract, so no figure is typed twice.
Above the ideal line | The team is behind - scope or impediments need attention at stand-up.
Below the ideal line | The team is ahead - capacity may be free for backlog items pulled forward.
Sprint 1 reading | Started flat (day 1 spent on schema design with nothing closable), then recovered and finished on plan.
Sprint 2 reading | Tracked close to ideal; the collision-concurrency test on days 4-5 cost more than estimated but was absorbed.
Sprint 3 reading | Fastest sprint - the admin console reused patterns already built, so the actual line stayed at or below ideal throughout.