## Sprint Backlog
Sprint ID / Sprint Name | User Story ID | User Story Description | Task ID | Task Description | Assignee | Estimated Effort (Hours) | Actual Effort (Hours) | Status | Start Date | End Date | Remarks
SP-01 / Sprint 1 - Foundation & Authentication | US-01 | As a system owner I need a relational schema so patient, doctor and appointment data is stored reliably | T-101 | Design DDL for users, patients, doctors, departments, rooms, appointments, payments | Rahul (Backend) | 10 | 9 | Done | 2026-06-01 | 2026-06-02 | Includes CHECK constraints for mobile format
SP-01 / Sprint 1 - Foundation & Authentication | US-01 | As a system owner I need a relational schema so patient, doctor and appointment data is stored reliably | T-102 | Add Postgres EXCLUDE constraints for doctor and room overlap | Rahul (Backend) | 6 | 8 | Done | 2026-06-02 | 2026-06-03 | btree_gist extension required; MySQL falls back to service checks
SP-01 / Sprint 1 - Foundation & Authentication | US-01 | As a system owner I need a relational schema so patient, doctor and appointment data is stored reliably | T-103 | Create JPA entities with Hibernate Validator annotations | Sneha (Backend) | 12 | 12 | Done | 2026-06-03 | 2026-06-05 | Lombok builders used to keep entities short
SP-01 / Sprint 1 - Foundation & Authentication | US-02 | As a visitor I want to register as a patient so that I can book appointments | T-104 | Registration API with unique email check | Sneha (Backend) | 8 | 8 | Done | 2026-06-05 | 2026-06-08
SP-01 / Sprint 1 - Foundation & Authentication | US-02 | As a visitor I want to register as a patient so that I can book appointments | T-105 | Registration form with confirm password and strong password rules | Aditya (Frontend) | 10 | 11 | Done | 2026-06-08 | 2026-06-09 | Password rule mirrored on client and server
SP-01 / Sprint 1 - Foundation & Authentication | US-03 | As a registered user I want to log in securely so that only I can see my records | T-106 | JWT issue and validation filter | Rahul (Backend) | 10 | 10 | Done | 2026-06-05 | 2026-06-08
SP-01 / Sprint 1 - Foundation & Authentication | US-03 | As a registered user I want to log in securely so that only I can see my records | T-107 | Spring Security config with role based URL rules | Rahul (Backend) | 8 | 7 | Done | 2026-06-08 | 2026-06-09
SP-01 / Sprint 1 - Foundation & Authentication | US-03 | As a registered user I want to log in securely so that only I can see my records | T-108 | Angular auth service, token interceptor and route guards | Aditya (Frontend) | 10 | 10 | Done | 2026-06-09 | 2026-06-10
SP-01 / Sprint 1 - Foundation & Authentication | US-04 | As a visitor I want to browse doctors and departments before logging in | T-109 | Public doctor and department endpoints with search | Sneha (Backend) | 6 | 6 | Done | 2026-06-09 | 2026-06-10
SP-01 / Sprint 1 - Foundation & Authentication | US-04 | As a visitor I want to browse doctors and departments before logging in | T-110 | Landing page with specialists and departments tables | Priya (Frontend) | 10 | 12 | Done | 2026-06-10 | 2026-06-12 | Department filter added on review feedback
SP-01 / Sprint 1 - Foundation & Authentication | US-05 | As a QA engineer I need seed data so the app is testable from the first run | T-111 | DataSeeder with admin, 3 departments, 4 doctors, 4 rooms | Faiz (QA) | 4 | 4 | Done | 2026-06-11 | 2026-06-12
SP-01 / Sprint 1 - Foundation & Authentication | US-05 | As a QA engineer I need seed data so the app is testable from the first run | T-112 | Smoke test pack for auth and public endpoints | Faiz (QA) | 6 | 6 | Done | 2026-06-11 | 2026-06-12
SP-02 / Sprint 2 - Booking, Collision & Payment | US-06 | As a patient I want to see which slots are free so that I can pick a convenient time | T-201 | Slot generation from doctor availability and slot length | Sneha (Backend) | 10 | 11 | Done | 2026-06-15 | 2026-06-16 | Past slots marked unavailable
SP-02 / Sprint 2 - Booking, Collision & Payment | US-06 | As a patient I want to see which slots are free so that I can pick a convenient time | T-202 | Slot picker UI with availability markers | Priya (Frontend) | 8 | 8 | Done | 2026-06-16 | 2026-06-17
SP-02 / Sprint 2 - Booking, Collision & Payment | US-07 | As a hospital I must never double-book a doctor or a room | T-203 | Collision validation service for doctor overlap | Rahul (Backend) | 10 | 10 | Done | 2026-06-15 | 2026-06-17 | Core acceptance criterion
SP-02 / Sprint 2 - Booking, Collision & Payment | US-07 | As a hospital I must never double-book a doctor or a room | T-204 | Room occupancy validation and free-room endpoint | Rahul (Backend) | 8 | 9 | Done | 2026-06-17 | 2026-06-18
SP-02 / Sprint 2 - Booking, Collision & Payment | US-07 | As a hospital I must never double-book a doctor or a room | T-205 | Concurrency test - two bookings for the same slot | Faiz (QA) | 8 | 10 | Done | 2026-06-18 | 2026-06-19 | Verified DB constraint catches the race
SP-02 / Sprint 2 - Booking, Collision & Payment | US-08 | As a patient I want to request an appointment and track its status | T-206 | Booking API returning PENDING appointment | Sneha (Backend) | 8 | 8 | Done | 2026-06-16 | 2026-06-18
SP-02 / Sprint 2 - Booking, Collision & Payment | US-08 | As a patient I want to request an appointment and track its status | T-207 | Booking page with room preference and reason | Priya (Frontend) | 10 | 10 | Done | 2026-06-18 | 2026-06-19
SP-02 / Sprint 2 - Booking, Collision & Payment | US-08 | As a patient I want to request an appointment and track its status | T-208 | Patient dashboard with appointment table and live status | Aditya (Frontend) | 10 | 10 | Done | 2026-06-19 | 2026-06-22
SP-02 / Sprint 2 - Booking, Collision & Payment | US-09 | As a patient I want to pay the consultation fee and get a receipt | T-209 | PaymentService abstraction and pending payment on booking | Rahul (Backend) | 6 | 6 | Done | 2026-06-22 | 2026-06-23
SP-02 / Sprint 2 - Booking, Collision & Payment | US-09 | As a patient I want to pay the consultation fee and get a receipt | T-210 | Card payment endpoint - Luhn check, store last 4 digits only | Rahul (Backend) | 10 | 12 | Done | 2026-06-23 | 2026-06-24 | PAN and CVV never persisted
SP-02 / Sprint 2 - Booking, Collision & Payment | US-09 | As a patient I want to pay the consultation fee and get a receipt | T-211 | Payment page with masked card input and terms checkbox | Priya (Frontend) | 10 | 10 | Done | 2026-06-24 | 2026-06-25
SP-02 / Sprint 2 - Booking, Collision & Payment | US-09 | As a patient I want to pay the consultation fee and get a receipt | T-212 | Printable receipt view with print stylesheet | Aditya (Frontend) | 8 | 9 | Done | 2026-06-25 | 2026-06-26 | Receipt typography locked against mobile auto-linking
SP-02 / Sprint 2 - Booking, Collision & Payment | US-10 | As a patient I want a refund when I cancel a paid appointment | T-213 | Cancel flow with automatic refund and admin remark | Sneha (Backend) | 8 | 8 | Done | 2026-06-25 | 2026-06-26
SP-03 / Sprint 3 - Admin Console, Search & UI | US-11 | As an admin I want to approve or reject appointment requests | T-301 | Approve and reject endpoints with mandatory remarks | Sneha (Backend) | 8 | 8 | Done | 2026-06-29 | 2026-06-30
SP-03 / Sprint 3 - Admin Console, Search & UI | US-11 | As an admin I want to approve or reject appointment requests | T-302 | Request queue table with inline actions and room assignment | Aditya (Frontend) | 10 | 10 | Done | 2026-06-30 | 2026-07-01
SP-03 / Sprint 3 - Admin Console, Search & UI | US-12 | As an admin I want CRUD screens for doctors, departments, rooms and patients | T-303 | Admin CRUD endpoints and validation rules | Rahul (Backend) | 12 | 12 | Done | 2026-06-29 | 2026-07-01
SP-03 / Sprint 3 - Admin Console, Search & UI | US-12 | As an admin I want CRUD screens for doctors, departments, rooms and patients | T-304 | Six-tab admin dashboard with forms and tables | Aditya (Frontend) | 14 | 15 | Done | 2026-07-01 | 2026-07-03
SP-03 / Sprint 3 - Admin Console, Search & UI | US-12 | As an admin I want CRUD screens for doctors, departments, rooms and patients | T-305 | Doctor years of experience field end to end | Priya (Frontend) | 4 | 4 | Done | 2026-07-03 | 2026-07-03
SP-03 / Sprint 3 - Admin Console, Search & UI | US-13 | As an admin I want to find records quickly and clean up in bulk | T-306 | Search bars - appointment ID/date, doctor ID/specialty, patient ID/date | Priya (Frontend) | 10 | 10 | Done | 2026-07-03 | 2026-07-06
SP-03 / Sprint 3 - Admin Console, Search & UI | US-13 | As an admin I want to find records quickly and clean up in bulk | T-307 | Bulk delete endpoints and multi-select tables | Rahul (Backend) | 8 | 8 | Done | 2026-07-06 | 2026-07-07
SP-03 / Sprint 3 - Admin Console, Search & UI | US-14 | As an admin I want to track whether a patient is admitted or discharged | T-308 | Patient status field with auto-discharge rule | Sneha (Backend) | 8 | 9 | Done | 2026-07-06 | 2026-07-07 | Auto-discharge runs when the patient list loads
SP-03 / Sprint 3 - Admin Console, Search & UI | US-14 | As an admin I want to track whether a patient is admitted or discharged | T-309 | Status column with admit and discharge actions | Priya (Frontend) | 6 | 6 | Done | 2026-07-07 | 2026-07-08
SP-03 / Sprint 3 - Admin Console, Search & UI | US-15 | As a user I want clear feedback for every action | T-310 | Global exception handler and error flattening | Rahul (Backend) | 6 | 6 | Done | 2026-07-01 | 2026-07-02
SP-03 / Sprint 3 - Admin Console, Search & UI | US-15 | As a user I want clear feedback for every action | T-311 | Popup service for success and error dialogs | Aditya (Frontend) | 6 | 6 | Done | 2026-07-02 | 2026-07-03
SP-03 / Sprint 3 - Admin Console, Search & UI | US-16 | As a hospital I want the portal to look professional and print correctly | T-312 | Native CSS theme, logo and navbar with home button | Priya (Frontend) | 10 | 11 | Done | 2026-07-08 | 2026-07-09 | No CSS framework used, per NFR-04
SP-03 / Sprint 3 - Admin Console, Search & UI | US-16 | As a hospital I want the portal to look professional and print correctly | T-313 | Responsive checks and print stylesheet QA | Faiz (QA) | 6 | 6 | Done | 2026-07-09 | 2026-07-10
SP-03 / Sprint 3 - Admin Console, Search & UI | US-17 | As a project team we need release artefacts | T-314 | Regression pass across all roles | Faiz (QA) | 8 | 8 | Done | 2026-07-09 | 2026-07-10
SP-03 / Sprint 3 - Admin Console, Search & UI | US-17 | As a project team we need release artefacts | T-315 | README, user manual and flowchart pack | Mustafa (Tech Lead) | 8 | 8 | Done | 2026-07-09 | 2026-07-10 | Delivered with the codebase zip
[5 empty] | TOTAL | 338 | 351
Legend: edit only the white cells. Status must be one of To Do / In Progress / Done. Effort is recorded in hours (1 story point = 4 hours for this team). Dates are working days; each sprint is 2 weeks / 10 working days.

## Sprint Summary
Sprint ID | Sprint Name | Start Date | End Date | Working Days | Tasks | Estimated (h) | Actual (h) | Done | Variance (h) | Velocity (h/day)
SP-01 | Sprint 1 - Foundation & Authentication | 2026-06-01 | 2026-06-12 | 10 | 12 | 100 | 103 | 12 | 3 | 10.3
SP-02 | Sprint 2 - Booking, Collision & Payment | 2026-06-15 | 2026-06-26 | 10 | 13 | 114 | 121 | 13 | 7 | 12.1
SP-03 | Sprint 3 - Admin Console, Search & UI | 2026-06-29 | 2026-07-10 | 10 | 15 | 124 | 127 | 15 | 3 | 12.7
| TOTAL |  |  |  | 40 | 338 | 351 | 40 | 13
All figures are formulas over the Sprint Backlog sheet - add a task there and this summary updates itself. Variance = Actual - Estimated (positive means the sprint over-ran its estimate).